## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Bibi Fatima Yadwad | 2026-09-01 | Configured Gemini model was unavailable for the new API setup | M1 | Bibi Fatima Yadwad | AI API / Configuration | Tested available Gemini model and updated the project configuration | 2026-09-01 | Closed | Resume extraction restored using the available Gemini model
2 | Bibi Fatima Yadwad | 2026-09-02 | Gemini API temporarily returned a 503/high-demand response during resume extraction | M1 | Bibi Fatima Yadwad | API Availability | Verified and used the local rule-based extraction fallback | 2026-09-02 | Closed | Resume processing remained functional when Gemini was unavailable
3 | Bibi Fatima Yadwad | 2026-09-05 | Raw job dataset contained senior, management, training/promotional and irrelevant records | M2 | Bibi Fatima Yadwad | Data Quality | Implemented dataset inspection, filtering and curation | 2026-09-06 | Closed | Final dataset contained 102 relevant technical opportunities
4 | Bibi Fatima Yadwad | 2026-09-06 | Dataset contained duplicate and highly similar job records | M2 | Bibi Fatima Yadwad | Data Duplication | Added duplicate and similar-title/company filtering | 2026-09-06 | Closed | Curated dataset was used for RAG indexing
5 | Bibi Fatima Yadwad | 2026-09-08 | Some semantic retrieval results were not sufficiently specific to the candidate's target role | M2 | Bibi Fatima Yadwad | Matching / Relevance | Included candidate skills, summary and target role in matching query and applied score-based ranking | 2026-09-09 | Closed | Baseline evaluation completed; further ranking improvements identified
6 | Bibi Fatima Yadwad | 2026-09-10 | Frontend dashboard required integration with backend profile, resume and job-matching workflows | M2 | Bibi Fatima Yadwad | Frontend / Backend Integration | Updated frontend API calls and integrated the career dashboard workflows | 2026-09-11 | Closed | Redesigned dashboard integrated with project backend
7 | Bibi Fatima Yadwad | 2026-09-22 | Skill Gap endpoint initially rejected requests when an invalid or placeholder job ID was provided | M3 | Bibi Fatima Yadwad | API / Validation | Tested the endpoint with valid job IDs returned by the job-matching service and integrated job selection with the skill-gap workflow | 2026-09-22 | Closed | Skill gap analysis now uses the selected job from current job matches
8 | Bibi Fatima Yadwad | 2026-09-22 | Skill Gap page was not integrated with the selected recommended job | M3 | Bibi Fatima Yadwad | Frontend / Backend Integration | Connected recommended job selection to the Skill Gap API and added job-specific analysis flow | 2026-09-22 | Closed | Selected job ID is passed to the skill-gap endpoint
9 | Bibi Fatima Yadwad | 2026-09-23 | Existing frontend UI was visually basic and did not clearly expose M3 career features | M3 | Bibi Fatima Yadwad | UI / UX | Redesigned the Career Companion interface with dashboard cards, improved navigation, job details and M3 feature sections | 2026-09-23 | Closed | Updated UI provides a more professional AI career platform experience
10 | Bibi Fatima Yadwad | 2026-09-23 | M3 feature sections such as Skill Gap, Application Studio and Interview Preparation were displayed only as placeholders | M3 | Bibi Fatima Yadwad | Feature Integration | Added M3 feature navigation and prepared the interface for Skill Gap, Application Studio and Interview Preparation workflows | 2026-09-23 | Closed | M3 modules are exposed through the redesigned Career Companion interface
11 | Bibi Fatima Yadwad | 2026-09-24 | Application Tracker initially required validation for application records before saving them to the database | M4 | Bibi Fatima Yadwad | API / Validation | Added validation for required application fields and tested application creation with valid and invalid inputs | 2026-09-24 | Closed | Application records are now validated before persistence
12 | Bibi Fatima Yadwad | 2026-09-24 | Application status changes were not initially reflected consistently across the tracker dashboard | M4 | Bibi Fatima Yadwad | Application Workflow | Updated application status handling and synchronized status changes with dashboard statistics | 2026-09-25 | Closed | Application lifecycle status and dashboard counts remain synchronized
13 | Bibi Fatima Yadwad | 2026-09-25 | Application tracker required support for multiple lifecycle stages such as Saved, Applied, Under Review, Shortlisted and Interview Scheduled | M4 | Bibi Fatima Yadwad | Feature Integration | Implemented and tested the complete application status workflow including Offer Received, Rejected and Withdrawn states | 2026-09-25 | Closed | Complete application lifecycle is available in the tracker
14 | Bibi Fatima Yadwad | 2026-09-26 | Deadline filtering required separate handling for upcoming, overdue and applications without deadlines | M4 | Bibi Fatima Yadwad | Filtering / Validation | Added deadline-based filtering and date validation for application records | 2026-09-26 | Closed | Users can filter applications by deadline status
15 | Bibi Fatima Yadwad | 2026-09-26 | Application dashboard statistics did not initially cover all required application states | M4 | Bibi Fatima Yadwad | Dashboard / Data Consistency | Updated dashboard aggregation logic to calculate total, active, deadline, interview, offer and rejection counts | 2026-09-27 | Closed | Dashboard provides consolidated application pipeline metrics
16 | Bibi Fatima Yadwad | 2026-09-27 | Tailored Resume generation required job-specific candidate information to avoid generic application content | M4 | Bibi Fatima Yadwad | AI / Feature Integration | Connected selected job requirements and verified candidate profile information to the tailored resume workflow | 2026-09-27 | Closed | Tailored resume generation uses selected job context and candidate profile data
17 | Bibi Fatima Yadwad | 2026-09-28 | Generated application content required protection against unsupported skills, achievements and experience | M4 | Bibi Fatima Yadwad | AI / Data Integrity | Applied candidate-profile-based prompting and validation rules to restrict generated content to verified information | 2026-09-28 | Closed | Application materials are designed to avoid unsupported candidate claims
18 | Bibi Fatima Yadwad | 2026-09-28 | Personalized Cover Letter workflow required integration with the selected application and target job | M4 | Bibi Fatima Yadwad | Feature Integration | Integrated selected job, candidate profile and application context into the cover letter generation workflow | 2026-09-29 | Closed | Cover letters are generated using job-specific application context
19 | Bibi Fatima Yadwad | 2026-09-29 | Application Tracker actions such as View, Edit and Delete required backend synchronization | M4 | Bibi Fatima Yadwad | Frontend / Backend Integration | Connected tracker actions with the corresponding backend application APIs and tested CRUD operations | 2026-09-30 | Closed | Application records can be viewed, updated and removed through the interface
20 | Bibi Fatima Yadwad | 2026-09-30 | Interview schedule information required integration with tracked application records | M4 | Bibi Fatima Yadwad | Application / Interview Integration | Added interview scheduling information to application records and integrated it with application tracking | 2026-09-30 | Closed | Interview information can be associated with the corresponding application
21 | Bibi Fatima Yadwad | 2026-10-01 | Application Tracker required verification of complete end-to-end application management workflow | M4 | Bibi Fatima Yadwad | End-to-End Testing | Tested application creation, status updates, filtering, deadline handling, editing, deletion and dashboard statistics | 2026-10-01 | Closed | Application management workflow validated successfully
22 | Bibi Fatima Yadwad | 2026-10-02 | M4 Application Tracker and Studio required final integration testing with existing M1-M3 modules | M4 | Bibi Fatima Yadwad | System Integration | Performed end-to-end integration testing across profile, resume, job matching, skill gap, application studio and interview workflows | 2026-10-02 | Closed | M4 functionality integrated with the existing Career Companion platform

## Sheet2
Logical
User Interface
Maintainability
Standards
Others